## Sheet1
ANNUAL ACTION+C19+A2:L9+A2:L10+A2:L27
S/N | ACTIVITY | LOCATION | OUTPUT | TIME FRAME |  |  |  | IMP AGENCIES |  | COST(GH¢) | SOURCE OF FUNDING
|  |  | INDICATORS |  |  |  |  | Lead Agency | Support
1 | Completion of 1No. 3Unit classroom block for motheodist K-G at Wamfie | Wamfie | 1 No.3unit classroom block completed and in use | x |  |  |  | GES | DA | 87405 | DACF
2 | Completion of 1No. 3Unit classroom block with office and storeroom for DA primary | Awuakrom | 1 No.3unit classroom block completed and in use | x |  |  |  | GES | DA | 83409.54 | DACF
3 | Completion of 1 No.6unit Classroom block with ancillary facilities for R/C primary | D/Akwamu | 1 No.6unit classroom block completed an in use | x | x |  |  | GES | DA | 120664.67 | DACF
4 | Completion of 1No.10 seater WC Tiolet | Sabikrom | WC tiolet completed and in use | x |  |  |  | CA | DA | 240.000.00 | DACF
5 | Construction of an Emmergency unit for District Hospital | Wamfie | Emmergency ward constructed and in use |  | x |  |  | DHD | CA | 210000 | DACF
6 | Construction of 1No. 4unit Classroom block for Wamfie Presby Primary | Wamfie | 4unit classroom constructed and in use | x | [5 empty] | 370000 | DACF
7 | Construction of 1No. 3 unit classroom block for DA JHS | Nseseresu/Asuhyiae | 3unit classroom constructed and in use |  | x |  |  | GES | DA | 185000 | DDF
8 | Rehabilitate and furnish 1No. 3 bedroom doctors bungalow for Health Centre | Dormaa Akwamu | Rehabilitation carried out and in use | x | x |  |  | DHD | DA | 90000 | RFG
9 | Mechanisation of 1No. Borehole at Akontanim | Akontanim | 1no. Borehole Mechanised |  |  | X |  | CA | DA | 12000 | IGF
10 | Reshaping of 50km of new and existing feeder road | District Wide | Rehsaping carried out in | x | x | x | x | DA | DA | 80000 | DACF
11 | Construction of 1No. 2 bedroom semi-detached staff quarters | Wamfie | Staff quarters completed and in use | x | x | x |  | DA | DA | 450000 | DACF
12 | Cladding of 1No. 6unit Pavilion at Abroso | Abroso | cladding completed and classroom in use |  | x |  |  | GES | DA | 227000 | DACF
13 | Rehabilitation of 5No. Boreholes | District Wide | Boreholes rehablitated and in use | x |  |  |  | GES | DA | 55000 | DACF
14 | Re-roofing of 1no. 6unit classroom | Wamfie | classroom block re-roofed and in use |  | x |  |  | GES | DA | 82000 | DACF
15 | Construction of 1No. CHPS Compound at Kofi-Nti | Kofi-Nti | CHPS Constructed and in use | x |  |  |  | DHD | D/A | 370000 | DDF
16 | Construction of 1No. 6unit classroom block at Kyeremasu | Kyeremasu | 1no 6unit classroom constructed and in use |  | x | x |  | GES | D/A | 500000 | DACF
17 | Provision of 350dual/mono desk to basic schools | Selected areas | 350 dual desk procured and in use | x | X | X |  | GES | D/A | 50000 | IGF/ DONOR FUND
18 | Repair and maintenance of Streetlights | Selected areas | Electricity extended | x | X | X | X | CA | D/A | 50000 | DACF
19 | Undertake afforestation Project ( Cashew Plantation | Baahkroom Mewerenfrefo Abetinsua | Afforestation project carried out | X | X | X |  | CA | AGRIC | 200000 | GPSNP
20 | Construction of 3.4 Km Kyeremasu -Kofibourshed Road | Kofibour | 3.4 km road constructed and in use |  |  | x |  | CA | WKS | 120000 | GPSNP
21 | Construction of 2 No. Dams/Dugout | Nseseresu & Asuhyiah | 2No. Dams/Dugout constructed and in use | x | x | x | x | CA | AGRIC | 600000 | GPSNP & DACF
22 | Construction of 1No. 2Bedrrom bungalow for the distrcit director | Wamfie | District Director bungalow constructed and in use |  |  | X |  | CA | DA | 420000 | DACF
23 | Construction of 2no. 2 Bedroom staff bungalow | Wamfie | Staff quarters completed and in use |  |  | X |  | CA | DA | 590.000.00 | DACF
24 | Completion of 1no. Midwives quarters | Akontanim | Midwives quarters completed and in use | x |  |  |  | DHD | DA | 50000 | GOG
25 | Furnishing of Mewerenfrewuo CHPS compound | Mewerenfrewuo | Furnishing completed and in usex |  | x |  |  | DHD | DA | 25000 | DACF
26 | Construction of DCEs bungalow | Wamfie | DCEs bungalow constructed and in use |  |  | X |  | CA | DA | 800000 | DACF
27 | Raise & distribute 100,000 cashew seedlings | Akontanim | 100,000 cashew seedling raised | X | X | X |  | Agric | DA | 160000 | IOM
28 | PROGRAMMES
29 | Financial Assistance to Brilliant and needy students/PWD | District wide | Brilliant but needy students assisted financially | x | x | x | x | SW&CD | GES | 60000 | GOG
30 | Support to National and Official Day celebrations(6th march,farmers day,Citizens Day,My first day in school) | District wide | National and Official Day celebrations supported | x | x | x | x | CA | DA | 100000 | DACF
31 | Preparation and implementation of District composite Action Plan & budget | Wamfie | District composite Plan & budget prepared and implemented |  |  |  | x | CA | DA | 10000 | IGF
32 | Maintenance of Office Equipment ,furniture,Fixtures & Vicheals | Wamfie | Office equipment maintained | x | x | x |  | CA | DA | 74000 | DACF
33 | Facilitate for the extablishment of Commmercial bank | Wanfie | Commercial Bank in Operation in the District |  | x | x |  | CA | GCB | 5000 | IGF
34 | Procurement of stationary and Office equipment | Wamfie | Office equipment purchased | x |  |  |  | CA | DA | 23682 | DDF
35 | Support to Community Initiated projects | District wide | Community initiated projects supported | x | x | x | x | Com'ty | DA | 184000 | DACF
36 | Monitoring of all programmes and projects | District wide | Programmes and projects monitored | x | x | x | x | DA | DA | 30000 | DACF
37 | Support to HIV and AIDS Programme | District wide | HIV and AIDS Programme supported | x | x | x | x | CA | DHD | 23000 | DACF
38 | Organise a public fora on AAP and budgeting | District Wide | Public fora organised | x | x | x | x | CA | DA | 10000 | IGF
39 | Form and train 20 women cooperative groups on LED | District wide | Household tiolets constructed and in use |  | x |  |  | DA | DA | 10000 | DACF
40 | Support Local Economic Development(LED,DCART,PFJ & PERD) | District wide | Local economic activities supported and in use | x | x | x | x | CA | DA | 100000 | DACF
41 | Capacity building &Manpower development of staff | wamfie | Capacity of staff enhansed and productivity enhansed | x | x | x | x | DA | DA | 110000 | DDF
42 | Planning,Budgeting and coordination Activities | Wamfie | Planing and budging activities carried out | x | x | x | x | DA | DA | 20000 | IGF
43 | Undertake a trainning for 300 women on preparation of blacksoap & liquid soap | District Wide | trainning done for 300 women |  |  | x |  | AGRIC | DA | 8000 | IGF
44 | Develope land for light industrial enclave | Wamfie | light industrial area developed and in use |  |  |  | x | CA | DA | 100000 | IGF
45 | Conduct surveillance/early warning systems on pest and diseases of crops quarterly | District Wide | surveillanve carried out on pets district wide | x | x | x | x | DADU | DA | 3000 | IGF
46 | Train 100 women on how to process Cassava, Plantain,cocoyam and Yam into powder | Distric Wide | No. of Women Trainned in cassava, Plantain, yam into powder | x |  |  |  | DADU | DA | 8000 | IGF
47 | Organise an Agriculture fair | District Wide | Agric Fair organised |  |  |  |  | DADU |  | 10000 | GOG
48 | Train 40 farmersa and 10 retailers on proper handling and use of agro-chemicals | District Wide |  |  | x |  |  | DADU | DA | 1000 | GOG
49 | Provide value services for actors of value chains to enhance their productivity | District Wide | Production is improved | x | x | x | x | DADU | DA | 2500 | GoG
50 | Support 5women & 1 Men groups to undertake farming on the planting for investment programme | District Wide | Women educated on government policies |  | x |  |  | DADU/ GENDER | DA | 1000 | IGF
51 | Conduct surveillance/early warning systems on pest and diseases of crops quarterly | District Wide | surveillanve carried out on pets district wide | x | x | x | x | AGRIC | DA | 3000 | IGF
52 | Organise quarterly community durbars on safe motherhood | District wide | Quarterly durber organised on safe motherhood | x | x | x | x | DHD | DA | 12000 | DACF
53 | Intensify education on top ten disease cases to reduce effect. | District wide | education carried out on top ten disease cases | x | x | x | x | DHD | DA | 4000 | DACF
54 | Conduct task force inspection visits to eliminate haphazard and unauthorized development | District wide | unauthorised development stopped |  |  | x | x | T&CP | DA | 4000 | IGF
55 | Organise demonstration exercise on disaster prevention and management in 6 Area Councils | District wide | Demonstration exercise carried out in 36 communities |  |  | x | x | NADMO | DA | 6000 | DACF
56 | Undertake health screening on food vendors and drinking spots | District wide | Health screening carried out |  | x |  |  | EH | DA | 3000 | DACF
57 | health promotion and sensitization in communities and schools | District wide | quarterly sensitiation on hygiene done | x | x | x | x | EH | DA | 4000 | DACF
58 | Organise monthly cleanup activities within the district | District wide | Clean-up organised | x | x | x | x | EH | DA | 10000 | IGF
59 | Organise Annual fee fixing resolution meeting and Gazetteing | Wamfie | fee fixing organised | x | x | x | x | CA | DA | 9000 | IGF
60 | Equip DVGs with fire fighting materials | Wamfie | DVGs equiped |  |  |  |  | NADMO | DA | 500 | IGF
61 | Facilitate MSMEs access to institutional Credit. | Wamfie | MSME have access to credit |  | x | x | x | NBSSI | DA | 1000 | IGF
62 | Implement LEAP and Support 250 PWDs | District wide | LEAP and PWD activities carried out | x | x | x | x | CD/SW | DA | 2000 | DACF
63 | Resolve issues relating to Vulnerability (child welfare/Aged/) | District Wide | vulnerabilty issues resolved | x | x | x | x | CD/SW | DA | 1000 | DACF
64 | Undertake youth sensitiation on effects of drug use and Teenage pregnancy | District Wide | Youth sensitiation carried out |  |  | x |  | CD/SW | DA | 12000 | DACF
65 | Develop planning schemes for 2 area councils | Asuotiano | Development schemes developed | x | x |  |  | T&CP | DA | 100000 | DACF
66 | Undertake development control and monitoring | District Wide | Development is controlled | x | x |  |  | T&CP | DA | 4000 | DACF
67 | Undertake street Naming and property addressing | Wamfie & Asuotiano | street naming and property carried out | x | x |  |  | T&CP | DA | 70000 | DACF
68 | Undertake training workshop for fire volunteers and DVG’s | District Wide | Trainning workshop carried out |  | x |  |  | NADMO | DA | 4000 | DACF
69 | Undertake tree planting exercise in 6 schools | Wamaafuo, Akontanim | Tree planting carried out | x |  |  |  | NADMO | DA | 80000 | DACF
70 | Undertake sensitization on bushfire and activities | District Wide | Sensitization carried out in all area councils |  |  | x |  | NADMO | DA | 6000 | IGF
71 | Support disaster management and Climate change activities | District wide | Climate change issues managed | x |  |  |  | NADMO | DA | 70000 | IGF
72 | Undertake p2 activities (Radio prg,com'ty score card,Open day,public hearings,stakeholders Engagements,Electoral Tour) | District wide | P2 activities implemented | x | x | x | x | CA | DA | 60000 | DACF
73 | Develop weekly revenue update on inflows | All area councils | Weekly revenue update displayed | x | x | x | x | FIN | DA | 100 | IGF
74 | Take steps to develop the tourism potencial within the district | Akontanim | Tourism potential developed |  |  |  | x | CA | Tourist Board | 2000 | IGF
75 | organise pay your levy champign in all area councils | District wide | Champign organised in all area councils | x | x | x | x | FIN | DA | 7000 | IGF
76 | Undetake capacity building programme(Staff, Unit Commtt,Plot Allocation Committee ) | Wamfie | Capacity of staff enhansed and productivity enhansed |  | x |  |  | CA | DA | 100000 | RFG
78 | Organise quiz competition in schools | District Wide | quize organised in 31 schools | x | x | x | x | GES | DA | 5000 | DACF
79 | Undertake Mop trainning on new curriculum programme | Wamfie | Trainning carried out on new curriculum |  |  |  |  | GES | DA | 12000 | GoG
80 | Organise statutory meetings of the Assembly | Wamfie | statutory meetings organised | x | x | x | x | C/A | DA | 60000 | DACF
81 | develop guideline for pregnancy prevention among school girls and facilitate re-entry after child birth | Wamfie | guideline developed and re-entry facilitated | x | x | x | x | GES | DA | 4000 | GOG/DACF
82 | Support to fight against illegal mining/maintain security | District Wide | Illegal Minning activities halted in the district |  | x | x | x | CA | DA | 50000 | DACF