## Sheet1
DORMAA EAST DISTRICT ASSEMBLY
COMPOSITE ANNUAL ACTION PLAN FOR 2021
S/N | ACTIVITY | LOCATION | OUTPUT | TIME FRAME |  |  |  | IMP AGENCIES |  | COST(GH¢) | SOURCE OF FUNDING
|  |  | INDICATORS |  |  |  |  | Lead Agency | Support
1 | Completion of 1No. 3Unit classroom block for motheodist K-G at Wamfie | Wamfie | 1 No.3unit classroom block completed and in use | x |  |  |  | GES | DA | 82563.87 | DACF
2 | Completion of 1No. 3Unit classroom block with office and storeroom for DA primary | Awuakrom | 1 No.3unit classroom block completed and in use | x |  |  |  | GES | DA | 98565.96 | DACF
3 | Completion of 1No. Police Station at Dormaa Akwamu | D/Akwamu | 1No. Police station completed and in use | x | x |  |  | CA | DA | 383410.86 | DACF
4 | Construction of 1No. Police station with ancillary facilities at Wamanafo | Sabikrom | 1No. Police station completed and in use |  | x |  |  | CA | DA | 538711.3 | DACF
5 | Construction of 1No. CHPS Compound at Asuotiano | Asuotiano | 1No. CHPS Compound constructed and in use |  |  |  | x | DHD | CA | 479935.04 | DACF
6 | Construction of 1No. 4unit Classroom block for Wamfie Presby Primary | Wamfie | 4unit classroom constructed and in use | x |  |  |  | GES | DA | 370000 | DACF
7 | Paving of 1800sqm Lorry station with open shed at Wamanafo | Wamanafo | Lorry station with open shed paved and in use |  |  |  | x | CA | DA | 200633 | RFG
8 | Construction of 1No. CHPS compound and staff quarters with ancillary facilities at Amanfe | Amanfe | 1No. CHPS Compound constructed and in use | x | x |  |  | DHD | DA | 315860 | DACF
9 | Construction of 1No. Ambulance office with ancillary facility at Wamfie | Wamfie | Ambulance office with ancillary facility constructed and in use | x | x | X | x | DHD | DA | 199951.5 | MP-DACF
10 | Reshaping of Wamanafo-Kuamakrom Feeder roads and others (28km) | Wamanafo-Kuamakrom and others | Rehsaping carried out | x | x | x | x | DA | DA | 19990 | DACF
11 | Completion of Office complex for Dormaa East District Assembly | Wamfie | Office complex constructed and in use | x | x | x | x | DA | DA | 300000 | DACF
12 | Furnishing of New Office complex | Wamfie | Furnishing completed and in usex |  |  |  | x | D/A | DA | 227000 | GOG
13 | Clearing and levelling of new office block and other selected roads (5km) | Wamanafo areas | clearing and levelling carried out |  | x | x |  | CA | D/A | 60000 | DACF
14 | Undertake afforestation Project ( Cashew Plantation | Baahkroom Mewerenfrefo Abetinsua | Afforestation project carried out | X | X | X |  | CA | AGRIC | 200000 | GPSNP
15 | Rehabilitation of 3.4 Km Kyeremasu -Kofibourshed Road | Kofibour | 3.4 km road constructed and in use |  |  | x |  | CA | WKS | 168714.91 | GPSNP
16 | Rehabilitation of of small Earth dam at Nseseressu | Nseseresu | Dams constructed and in use | x | x | x | x | CA | AGRIC | 487786.34 | GPSNP
17 | Raise & distribute 100,000 cashew seedlings | Akontanim | 100,000 cashew seedling raised | X | X | X |  | Agric | DA | 160000 | IOM
Sub-Total | [9 empty] | 4293122.78
PROGRAMMES
18 | Financial Assistance to Brilliant and needy students/PWD | District wide | Brilliant but needy students assisted financially | x | x | x | x | SW&CD | GES | 60000 | GOG
19 | Support to National and Official Day celebrations(6th march,farmers day,Citizens Day,My first day in school) | District wide | National and Official Day celebrations supported | x | x | x | x | CA | DA | 100000 | DACF
20 | Preparation and implementation of District composite Action Plan & budget | Wamfie | District composite Plan & budget prepared and implemented |  |  |  | x | CA | DA | 10000 | IGF
21 | Maintenance of Office Equipment ,furniture,Fixtures & Vehicles | Wamfie | Office equipment maintained | x | x | x |  | CA | DA | 74000 | DACF
22 | Facilitate for the extablishment of Commmercial bank | Wanfie | Commercial Bank in Operation in the District |  | x | x |  | CA | GCB | 5000 | IGF
23 | Procurement of stationary and Office equipment | Wamfie | Office equipment purchased | x |  |  |  | CA | DA | 23682 | DDF
24 | Support to Community Initiated projects | District wide | Community initiated projects supported | x | x | x | x | Com'ty | DA | 184000 | DACF
25 | Monitoring of all programmes and projects | District wide | Programmes and projects monitored | x | x | x | x | DA | DA | 30000 | DACF
26 | Support to HIV/AIDS and Covid 19 Programme | District wide | HIV/AIDS and Covid-19 Programme supported | x | x | x | x | CA | DHD | 23000 | DACF/COVID-19
27 | Organise a public fora on AAP and budgeting | District Wide | Public fora organised | x | x | x | x | CA | DA | 10000 | IGF
28 | Form and train 20 women cooperative groups on LED | District wide | 20 women coperative groups on LED conducted |  |  |  |  | DA | DA | 10000 | DACF
29 | Support Local Economic Development(DCART,PFJ & PERD) | District wide | Local economic activities supported and in use | x | x | x | x | CA | DA | 100000 | DACF/MAG
30 | Capacity building &Manpower development of staff | wamfie | Capacity of staff enhansed and productivity enhansed | x | x | x | x | DA | DA | 110000 | DDF
31 | Undertake a trainning for 300 women on preparation of blacksoap & liquid soap | District Wide | trainning done for 300 women |  |  | x |  | AGRIC | DA | 8000 | IGF
32 | Develope land for light industrial enclave | Wamfie | light industrial area developed and in use |  |  |  | x | CA | DA | 100000 | IGF
33 | Educate women on government policies ( Domestic violence bill, constitution, good parenting) and rights to participate in decision making | District Wide | Women educated on government policies | x |  |  |  | CA | DA | 8000 | IGF
34 | Conduct surveillance/early warning systems on pest and diseases of crops quarterly | District Wide | surveillanve carried out on pets district wide | x | x | x | x | DADU | DA | 3000 | IGF
35 | Engagement with women on challenges faced by women coperatives in cocoa farming | Distric Wide | Women coporatives engaged on cocoa farming challenges | x |  |  |  | DADU | DA | 8000 | IGF
36 | Organise an Agriculture fair | District Wide | Agric Fair organised |  |  |  |  | DADU |  | 10000 | GOG
37 | Conduct taskforce inspection visits to eliminate haphazard and unauthorized development | District Wide | Taskforce inspection carried out on haphazard development |  |  | x | x | T&CP | DA | 4000 | IGF
38 | Support 5women & 1 Men groups to undertake farming on the planting for investment programme | District Wide | Women educated on government policies |  | x |  |  | DADU/ GENDER | DA | 1000 | IGF
39 | Organise quarterly community durbars on safe motherhood | District wide | Quarterly durber organised on safe motherhood | x | x | x | x | DHD | DA | 12000 | DACF
40 | Intensify education on top ten disease cases to reduce effect. | District wide | education carried out on top ten disease cases | x | x | x | x | DHD | DA | 4000 | DACF
41 | Ensure safety regulations are followed during construction of public and government projects | District wide | Safety regulations followed during construction | x | x | x | x | NADMO | DA | 1000 | DACF
42 | Planting of trees to serve as wind breaks in schools and communities | District wide | Tree planting carried out | x | x |  |  | NAMO | DA | 2000 | DACF
43 | Organise demonstration exercise on disaster prevention and management in 6 Area Councils | District wide | Demonstration exercise carried out in 36 communities |  |  | x | x | NADMO | DA | 6000 | DACF
44 | Undertake health screening on food vendors and drinking spots | District wide | Health screening carried out |  | x |  |  | EH | DA | 3000 | DACF
45 | Hygiene promotion and sanitation sensitization in communities and schools | District wide | quarterly sensitiation on hygiene done | x | x | x | x | EH | DA | 4000 | DACF
46 | Regulate the activities of information centers, drinking bars and spinners in the district to ensure noise is controlled | District wide | Noise is controlled and environment frr fromm all forms of pollution | x | x | x | x | EH | DA | 5000 | IGF
47 | Organise monthly cleanup activities within the district | District wide | Clean-up organised | x | x | x | x | EH | DA | 10000 | IGF
48 | Organise Annual fee fixing resolution meeting and Gazetteing | Wamfie | fee fixing organised | x | x | x | x | CA | DA | 9000 | IGF
49 | Facilitate MSMEs access to institutional Credit. | Wamfie | MSME have access to credit |  | x | x | x | NBSSI | DA | 1000 | IGF
50 | Implement LEAP and Support 250 PWDs | District wide | LEAP and PWD activities carried out | x | x | x | x | CD/SW | DA | 2000 | DACF
51 | Resolve issues relating to Vulnerability (child welfare/Aged) | District Wide | vulnerabilty issues resolved | x | x | x | x | CD/SW | DA | 1000 | DACF
52 | Undertake youth sensitiation on effects of drug use and Teenage pregnancy | District Wide | Youth sensitiation carried out |  |  | x |  | CD/SW | DA | 12000 | DACF
53 | Develop planning schemes for 2 area councils | Asuotiano | Development schemes developed | x | x |  |  | T&CP | DA | 100000 | DACF
54 | Undertake development control and monitoring | District Wide | Development is controlled | x | x |  |  | T&CP | DA | 4000 | DACF
55 | Undertake street Naming and property addressing | Wamfie & Asuotiano | street naming and property carried out | x | x |  |  | T&CP | DA | 70000 | DACF
56 | Undertake training workshop for fire volunteers and DVG’s | District Wide | Trainning workshop carried out |  | x |  |  | NADMO | DA | 4000 | DACF
57 | Undertake sensitization on effects of sand winning and bush fires | District Wide | Citizens informed on the effects of sand winning and bush fires | x |  | x |  | NADMO | DA | 1000 | GOG
58 | Facilitate for the establishment of a gari processing factory | Praprababida | Gari processing factory established | x |  |  |  | CA | DA | 70000 | IGF
59 | Undertake p2 activities (Radio prg,com'ty score card,Open day,public hearings,stakeholders Engagements,Electoral Tour) | District wide | P2 activities implemented | x | x | x | x | CA | DA | 60000 | DACF
60 | Develop weekly revenue update on inflows | All area councils | Weekly revenue update displayed | x | x | x | x | FIN | DA | 100 | IGF
61 | Take steps to develop the tourism potencial within the district ( Mystery stone ) | Akontanim | Tourism potential developed |  |  |  | x | CA | Tourist Board | 2000 | IGF
62 | organise pay your levy campaign in all area councils | District wide | Champign organised in all area councils | x | x | x | x | FIN | DA | 7000 | IGF
63 | Undetake capacity building programme(Staff, Unit Commtt,Plot Allocation Committee ) | Wamfie | Capacity of staff enhansed and productivity enhansed |  | x |  |  | CA | DA | 100000 | RFG
64 | Organise quiz competition in schools | District Wide | quize organised in 31 schools | x | x | x | x | GES | DA | 5000 | DACF
65 | Organise statutory meetings of the Assembly | Wamfie | statutory meetings organised | x | x | x | x | C/A | DA | 60000 | DACF
66 | Develop guideline for pregnancy prevention among school girls and facilitate re-entry after child birth | Wamfie | guideline developed and re-entry facilitated | x | x | x | x | GES | DA | 4000 | GOG/DACF
67 | Support to fight against illegal mining/maintain security | District Wide | Illegal Minning activities halted in the district |  | x | x | x | CA | DA | 50000 | DACF
68 | Ensure parking improvement along the major highway | District Wide | Parking along major high way Improved | x | x |  |  | CA | DA | 5000 | DACF
69 | Undertake roadside safety measures ( clearing of road side bushes, street lighting repairs) | District Wide | Road side safety measures carried out |  | x | x |  | CA | DA | 4000 | DACF
70 | Improve street lighting, road markings and road signage | Distrit Wide | Street lighting, road markings and road signage Improved | x | x |  |  | CA | DA | 4000 | DACF
71 | Reshaping of 50km of new and existing feder roads | Selected Areas | 50km of new and existing feeder roads rehaped |  | x |  |  | CA | DA | 80000 | RFG
Sub-Total | [9 empty] | 1583782
Grand-Total | [9 empty] | 5876904.78